## Gantt Chart w % Complete (hidden)
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6
Sprint 1
| Project Idea pitch | 2018-05-01 | 1 | 2018-05-19 | 19 | 19 | 0 | Gabriel | 100%
| Investigate the requirements | 2018-05-01 | 1 | 2018-05-19 | 19 | 15.2 | 3.8 | Robert | 80%
| Write a Project Plan | 2018-05-01 | 1 | 2018-05-19 | 19 | 11.4 | 7.6 | Robert | 60%
| Write a URS | 2018-05-01 | 1 | 2018-05-19 | 19 | 7.6 | 11.4 | Ibrahim | 40%
| Sprint 2 Goal | 2018-05-01 | 1 | 2018-05-19 | 19 | 3.8 | 15.2 | Gabriel | 20%
Sprint 2
| Develop user stories | 2018-05-20 | 20 | 2018-06-09 | 21 | 21 | 0 | Gabriel | 100%
| Write a Design Document | 2018-05-20 | 20 | 2018-06-09 | 21 | 16.8 | 4.2 | Robert | 80%
| Start building environment | 2018-05-20 | 20 | 2018-06-09 | 21 | 12.6 | 8.4 | Ibrahim | 60%
| Sprint 3 Goal | 2018-05-20 | 20 | 2018-06-09 | 21 | 8.4 | 12.6 | Ibrahim | 40%
Sprint 3
| Start Testing Client app | 2018-06-10 | 10 | 2018-06-29 | 20 | 20 | 0 | Robert | 100%
| Pen-testing and Security | 2018-06-10 | 10 | 2018-06-29 | 20 | 16 | 4 | Ibrahim | 80%
| Write a Manual | 2018-06-10 | 10 | 2018-06-29 | 20 | 12 | 8 | Gabriel | 60%
| Write Process Report | 2018-06-10 | 10 | 2018-06-29 | 20 | 8 | 12 | Robert | 40%
| Finalize URS & DD | 2018-06-10 | 10 | 2018-06-29 | 20 | 4 | 16 | Ibrahim | 20%
Sprint 4
| Deliver Project | 2018-07-01 | 1 | 2018-07-07 | 7 | 7 | 0 | Gabriel | 100%
| Assessment Week | 2018-07-01 | 1 | 2018-07-07 | 7 | 5.6 | 1.4 |  | 80%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart (hidden)
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Sprint 1
| Project Idea pitch | 2020-05-06 | 2020-05-11 | 4 | Gabriel | 100% | bar: WEEK 10 W to WEEK 11 F; WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 15 F
| Investigate the requirements | 2020-05-07 | 2020-05-18 | 8 | Robert | 80% | bar: WEEK 10 Th to WEEK 12 M; WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 15 F
| Write a Project Plan | 2020-05-11 | 2020-06-20 | 30 | Robert | 60% | bar: WEEK 11 M to WEEK 12 W; WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 15 F
| Write a URS | 2020-05-18 | 2020-05-28 | 9 | Ibrahim | 40% | bar: WEEK 11 M to WEEK 15 F
| Sprint Goal 2 | 2020-05-28 | 2020-05-29 | 2 | Gabriel | 20% | bar: WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 15 F
Sprint 2
| Develop user stories | 2020-06-01 | 2020-06-20 | 15 | Robert | 100% | bar: WEEK 13 Th to WEEK 15 F
| Write a Design Document | 2020-06-01 | 2020-06-20 | 15 | Gabriel | 80% | bar: WEEK 13 Th to WEEK 16 F
| Start building the environment | 2020-06-04 | 2020-06-20 | 12 | Ibrahim | 60% | bar: WEEK 13 Th to WEEK 13 F; WEEK 14 Th to WEEK 16 F
| Sprint Goal 3 | 2020-06-08 | 2020-06-09 | 2 | Ibrahim | 40% | bar: WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 15 F
Sprint 3
| Start Testing Client app | 2020-06-08 | 2020-06-20 | 10 | Robert | 100% | bar: WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 16 F
| Pen-testing and Security | 2020-06-08 | 2020-06-20 | 10 | Ibrahim | 80% | bar: WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 16 F
| Write a Manual | 2020-06-08 | 2020-06-20 | 10 | Gabriel | 60% | bar: WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 16 F
| Write a Process Report | 2020-06-08 | 2020-06-20 | 10 | Robert | 40% | bar: WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 16 F
Sprint 4
| Assessment Week | 2020-06-22 | 2020-06-26 | 5 | Gabriel | 80% | bar: WEEK 13 Th to WEEK 13 F; WEEK 15 M to WEEK 15 F
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])